## HSA-Customer
sr | Screens | description | Comment |  | Time In Hour
1 | Registration | Working
2 | Login | Working
3 | Login - google | not working | need to fix |  | 6
4 | Login - facebook | not working | need to fix |  | 6
5 | otp verification screen | OTP sending works inconsistently |  |  | 5
- don't shows a timer on screen as per design
6 | Dashboard screen | Location missing | - Not showing current location - Don't have option to change location | it has been asked to remove - Dhananjay
7 | subcategories | functionality working
8 | User location selection | Not implemented
9 | Create request | - select service and sub service label are not visible just showing dropdown
|  | - Current location is not used as default address while creating request, its mandatory to select address from dropdown, or should use one address as default address from saved addresses. - FrontEnd Fixes Required | when user first register, he should be prompt to add address and should set that as a default address | Need more explaination
|  | - Search box is not visible on starting search for location - design issue | design issue
|  | - on tap of map multiple pointer get added on map - it show more that one pointer | app side
- on selecting address from drop down, location pointer on map is not changing it still pointing to current location basedon user current geolocation
|  | - on upload image shows loading screen, can not go adhead with create request - Need to Debug | its too slow, will irritate user |  | 10
|  | - on adding promo code, not showing error or success |  |  | 3
| Create request: payment flow | - on selecting card payment and pay, it's gives error |  |  | 7
|  | - If request is raised and servicer provider don't accept that in set threshold time which is 60 sec now, - its show amount as NAN, should show N.A |  |  | 4
10 | Tracking | After Service Request Tracking page navigation after close that page. | Not cleared - Dhananjay | Need more explaination
11 | Address | On add and edit address lat-long selection functionality not cleared. | Not cleared - Dhananjay | Need more explaination
12 | Address Search | Address search on service request page, as of now we given existing address search functionality need further explaination |  | Need more explaination | 5
13 | My Profile - manage Address | - it save's text address only, should save lat and long as well |  | Need more explaination | 4
|  | - on add address screen, on tapping submit button multiple times, its add address those many times | address should be unique
14 | My Profile - manage Cards | - It showing hardcoded list of cards | Card feature not implemented |  | 8
- deleting card not working
- add card not working and design is not proper
- default card selection not implemented
15 | My Profile - Change Personal info | - changing mobile no - otp verification is not implemented |  |  | 8
16 | My Profile - Credits | - Credit screen is not visible on motog5 plus
|  | - Please check credit point used while payment of service request, I don't think it is implemented |  |  | 8
17 | FAQ | functionality working
design issue - here is no scroller coming if content is more than view port tested on motog5 plus
18 | Refer a friend |  | Not implemented by developer | estimated in service provider
19 | Category | Category Search Not Implemented | DONE |  | 5
20 | Create Request Page | GPS Auto detection not implemented
21 | Notifications | Not Implemented |  |  | 8
22 | Live Tracking Feature Missing |  | estimation given in service provider app
23 | Instagram (logo plus feature) missing, Also, G+ is now no longer working (we should get it removed after client confirmation) |  |  |  | 8
24 | Error Msg (Popups) | "Tranaction Failed" ------> "Transaction Failed"
95
Web -
1. Dashboard - some calculation pending from backend - so graphical represention is pending, other block completed.
2. Need to check reports - after complete calculations.
3. Need to change - Edit service request - As per mobile app changes.
these above points are pending, in admin panel

## HSA-Service Provider
sr | Screens | Comment |  |  | Time in Hour
1 | Splash Scree | working
2 | Login- new user | working | user role should be service provider
| Login- existing user | working | user role should be service provider
3 | Dashboard/ My task | - I registered as a new service provider and found other service provider's request in my profile |  |  | 3
|  | - Could not see Service Amount on dahsboard screen |  |  | 2
|  | - On rejecting request it shows message `Service request accepted`. | should show proper message and a box to add comment reason for rejecting. |  | 2
4 | Request Details - Request Summary | - Could not see service category, order id, media files - Customer location is not shown on map, should show pointer on map |  |  | 4
5 | Request Summary - Request/Process Status - reject case | - If service provider reject request, it showing message `service request accepted`. - if request is rejected there should be way to add comment |  |  | 6
6 | Request Summary - Request/Process Status - Accept case | - location tracking is not implmented to show live location of service provider on click of a start button - BackEnd + FrontEnd |  | Need to do R&D | 25
|  | - there is no provision for service provider to notifiy customer that he is reached to customer's address |  | Need more explaination | 4
|  | - there is no provision to notify customer service provider reached to customer address |  | Need more explaination | 2
|  | - there is no provison to cancel request once accpeted in case of emergency |  | Need more explaination | 4
|  | - If service provider reaches customer location and doesn’t find any contact person they can mark status as “No Response”. In this case customer will need to raise new request. |  | Need more explaination | 3
7 | Request Summary - Submit Quote | - there is no way to remove material once added |  |  | 4
8 | Request Summary - Quote Accepted | - there is no way to reschedule task after accepting Quote |  | Need more explaination | 6
|  | - there is no way to requote as mentioned in srs |  | Need more explaination | 6
9 | Request Summary - Payment | - Card payment not working |  | Not implemented
|  | - for COD payment service provide don't have option to confirm payment done or not |  | app side
10 | Request Summary - Customer review | - added review for customer is not saved, show add review option again |  | app side
11 | My profile - address | working
12 | My profile - personal info | user should not able to update email, mobile and city, it should be managed by administrator |  |  | 5
13 | My profile - FAq | design issues if more faq added, not able scroll
14 | My profile - Contact | design issues if more contact request added
15 | Refer a friend |  | not functioning |  | 5
16 | Statistics Page | Missing Credit Card Payment received bar - Front + BackEnd |  |  | 8
17 | Notification Feature | Not Implemented |  |  | 12
| Overall Estimated Time |  |  |  | 101