## Consumer App
WORK BREAKDOWN STRUCTURE - Service Provider App
PROJECT TITLE |  | HSA | Responsible | DATE | 26-08-2019
COMPANY NAME |  | NEOSOFT TECHNOLOGIES |  | PROJECT MANAGER | SANDIP GHADGE
WBS NUMBER | TASK TITLE | DURATION (hrs) |  | DURATION (Weeks) | REMARKS
done
1 | Users |  | Abhishek Jaiswal | 2018-02-09 |  | on going
1.1 | Splash Screen | 1 |  |  |  | pending
1.2 | post spalsh screen | 0
1.3 | signup using mobile and otp verification and resend otp | 4
1.4 | signup using google | 24
1,5 | signup using facebook | 24
1,6 | complete profile details | 1
1.7 | login using mobile | 0 |  |  | working
2 | Dashboard |  | Ashwini | 2019-09-09
2.1 | dashboard screen | 2
2.2 | Left side panel option | 1 |  | 24/9/2019, 25/9/2019, 26/9/2019, 27/9/2019 | working, fix font issue in one plus
2.3 | Search services (with auto sugestion) | 9 |  |  | New functionality
2.3.1 | Intergation of Google Maps (Google API key for the Maps will be provided by client) | 9 | shushant |  | New functionality
2.4 | showing current location using gps or changing | 18 | shushant
2.5 | sub category listing | 1
3 | Create Request |  | Abhishek | 18-9-208
3.1 | show current Location on map by default and manual | 18
3.2 | upload 5 photo and a video | 5 | ashwini
3.3 | apply promocode | 1 |  |  | Validation issue
3.4 | fill details and request now | 0 | ashwini |  | working
3.5 | show acceptance screen | 1
3.6 | show try again if request not accepted | 1
3.7 | show service provider location and details on acceptance on map (Only showning othere party's location, NO live tracking) | 5
3.7.1 | live location tracking | 30 | shushant |  | R& D
4 | My request screen |  | Ashwini | 2019-11-09
4.1 | list request by date and new, ongoing and past | 4 |  |  | Dashboard/My Tasks Screen
4.2 | accept request | 4
4.3 | reject request with reason | 9 |  | 24/9/2019
4.4 | cancel request with comment | 9 |  | 24/9/2019
5 | Request Detail |  | ashwini
5.1 | show request summary | 1 |  | 24/9/2019
5.2 | request status screen | 1 |  | 24/9/2019
5.3 | service request accepted | 1 |  | 24/9/2019
5.4 | service provider arrived | 1 |  | 24/9/2019
5.5 | provide service qoute | 1 |  | 30/9/2019
5.6 | accept or reject qoute | 1 |  | 30/9/2019
5.7 | task done with checking images and video | 5 |  | 30/9/2019, 3/10/2019 | have to fix style issue
5.8 | payment done - autimatic using card or by cash | 12
5.8.1 | Payment gateway Integration | 10 |  |  | Rough estimation.final estimation will depend on the payment gateway suggested by client.
5.9 | review and rating | 9 | shushant | 30//9/2019
5.10 | Complaints and resolution | 4 | shushant | 30//9/2019
6 | My Profile Screen |  | Ashwini Kadam | 2019-06-09
6.1 | manage address | 4 |  |  | Multiple locations
6.3 | manage personal information | 4
6.4 | change language | 15 | ashwini |  | arabic drawer position change left, co-ordinate with vertika
6.5 | credits | 2
7 | contact and sharing
7.1 | Contact Us | 1 | Ashwini Kadam
7.2 | FAQ | 1 | Ashwini Kadam
7.3 | Refer a friend - facebook, twitter, instagram, google | 10 | Ashwini Kadam | 14/9/2019
8 | Notification |  | shushant rathore | 24-9-2019
8.1 | on request accept by service provider | 2
8.1.1 | Intergating Firebase module for Notifications | 18
8.2 | start journey, cancel journey, reach journey, no response | 2
8.3 | qoute sent by service provider | 2
8.4 | task done by service provider | 2
8.5 | payment done | 2
9 | arabic version |  | Pratham | 2019-12-09
| Total hrs | 292
| Total Days (9 hours/day) | 32.4444
| Total Weeks (5days/week) | 6.4889

## SP-issue
| issue | status | Reported by | Developer comment | Time(Hrs) | Developer2 comment | PM
Login
1 | otp auto detect while login | fixed | Sandip | Done |  | fixed
2 | login screen - cursor should be center align for country code and mobile no both | Done | Sandip |  |  | fixed
3 | Home Services look like cut on login screen | Done | Sandip | Done |  | fixed
4 | Validation on login screen | open | Ganesh |  |  | Pending
Left side Nav
1 | if link from left side bar, then gray background should wrap complete width | Done | sandip | Done |  | fixed
2 | add material chnage background of cancel button to light gray - make it same everywhere same reject button | Done | Sandip | Done |  | fixed
3 | Statistics:hamburger icon(navigation drawer) click is not working | fixed | Ganesh | Done |  | fixed
4 | Statistics:credit card payment recieved is not shown properly | fixed | Ganesh | Done |  | fixed
5 | Add address should be updated as discussed like consumer app, with fields location, complete address, address type, city and zip code | Done | Sandip | Done | 3 | fixed
6 | Change edit address as discussed like consumer app | Done | Sandip | Done | 4 | fixed
7 | Add address screen city dropdown is empty so can not create new address | Done |  | Done |  | fixed
8 | edit address show location pointer to current address, which should show to actual address | Done |  | Done |  | fixed
9 | in edit address location is still showing empty, as discussed before it should show actual address | Done |  | Done |  | fixed
10 | in edit address if i click on change address and click on use current location, nothing happens, it should set current location | Done |  | Done |  | fixed
11 | If search location on map it shows location pointer on map which is correct, but now if i move location pointer and save address. it still not saving updated pointer location it show location which found in search | Done |  | Done |  | fixed
Dashboard
2 | My task - new : if no task should show message accordingly | fixed | Pushkar | Done |  | fixed
3 | My Task - completed : star rating not aligned properly | fixed | Pushkar | Done |  | fixed
4 | My Task - completed : on click of star rating app is getting crashed | fixed | Pushkar | Done |  | fixed
5 | Task Details Page: Date is not in proper format(refer consumer app) | Done | Pushkar | Done |  | fixed
6 | Task Details Page: Images are not visible | fixed | Pushkar | Done |  | fixed
7 | Review should be done after completing task | fixed | Pushkar | Done |  | fixed
8 | Drawer issue | fixed | Sandip | Done
9 | My Tasks text is not centered, it has more top margin, remove top margin | Done | Sandip | Done |  | fixed
10 | on my task screen order should be Category, sub-category and then date | Done | Sandip |  |  | fixed
My Tasks
1 | On rejecting tasks, it still gives 2 options (Accept/Reject) | fixed | Pushkar | Done
2 | The task info should have the taskName as well, to make it clear. Also, the SRS has the status of task written in info details. | fixed | Pushkar | Done
3 | Ongoing: specific task can not open | fixed | Ganesh | Done | 1 | fixed
4 | Completed: Its always show 2-star rating | fixed | Ganesh | Done | 1 | fixed
5 | Ongoing : Date is not showing on this screen | fixed | Ganesh | Done | 1 | fixed
6 | Contact Screen:Customer Name, Contact Number and Address is not showing proper format | fixed | Ganesh | Done | 2 | fixed
7 | New:Rejecting task functionality is not working(id is not getting to backend) | Done | Ganesh | Done | 2
8 | New:reload functionality is not working | Done | Ganesh |  |  | fixed
9 | New:city and description is not showing properly | Done | Ganesh
Task Detail
1 | Even after completing any progress from Task Details screen, it still shows to do same operation (need to move to the next step) | Done | Pushkar | Done
2 | Submit button and stars should be disabled untill the required step. | fixed | Pushkar | Done |  | fixed
3 | After payment done the rating functionality not working | Done | Ganesh | Done |  | fixed
4 | Add Quotes details: 1) quantity and cost : should be able to enter number only - change keypad 2) dropdown has only material option to choose - change keypad | fixed | sandip | Done |  | fixed
5 | comments section get hidden behind submit, there should be space between comment box and submit button | Done | sandip | Done | 2 | fixed
6 | Service cost should be number only - change keypad | Done | sandip | Done |  | fixed
7 | time required in days -should be number only- change keypad | Done | sandip | Done |  | fixed
8 | in add material , material dropdown should have choose material text by default | Done | sandip | Done | 0.5 | fixed
9 | in add material, number and its place holder overlaps | Done | sandip | Done |  | fixed
10 | CANCEL button against 'Leave for job' is not working | Done | Pushkar | Done | 1 | fixed
11 | After No response, task must display as DELETED/CANCELED in the task details screen | Done | Pushkar |  | 3
12 | Once Quote is provided, the button should say "Requote" if provider wants to updated | fixed | Pushkar | Done |  | fixed
13 | Video is not uploading in task done screen | Done | Vartika |  | 3 | fixed
14 | once task done pic are uploaded and If I refresh app screen, it doesn't show uploaded images so I have re upload images | Done | Sandip |  | 3 | fixed
15 | App crash at add address and manage address | Done | Ganesh | Done | 5 | fixed
16 | Add pull to refresh on task detail screen | Done | Sandip | Done | 1 | fixed
17 | If I am in new screen and accept request and then change task status to leave for job it shows message reached, cancel and no response now I move back to dashboard screen it still show request in new tab with accept and reject option. it should maintain state | Done | Sandip | Done | 3 | fixed
18 | Consumer rejected Qoute but the green tick is shown against the Quate Accepted Label | Done | Pushkar |  |  | fixed
19 | if I click on any request in ongoing task list it showing message: Cannot read property 'toObject' of null | Done | Sandip | Done |  | fixed
Statistics
1 | showing left side down arrow | fixed | Ganesh | Done |  | fixed
Welcome Screen
1 | Home Services logo needs to be adjusted (cuts at the bottom text) | Done | Pushkar |  | 1 | fixed
3
2 | Change Language Dropdown overlaps "Refer a friend" tab [dropdown can go down on its click] | Done | Pushkar | Done | 2 | fixed
Change Language
1 | After change language the confirmation popup not closed | Done | Ganesh |  | 3 | fixed
2 | spelling mistake of arabic language | Fixed | Ganesh |  | 2 | fixed
3 | change Language: message is showing outside of the alert box | Done | Ganesh |  |  | fixed
4 | change Language: After change language user need to close app and start again | Done | Ganesh | Done |  | fixed
Profile
1 | Manage Address: when clicked on that app getting closed | Done | Ganesh |  | 4 | fixed
2 | Personal Information: city can not be updated | Done | Ganesh |  |  | fixed
3 | Edit Address: change place holder name in Address | Done | Ganesh |  |  | fixed
| Edit Address: In address textarea is not showing old address which is already set by provider | Done | Ganesh |  |  | fixed
Manage Material
1 | Add material: price -should be number only- change keypad | Done | Ganesh |  | 1 | fixed
2 | Add material: After Cancel button clicked its show previous data which is entered by user | Done | Ganesh |  | 1 | fixed
3 | update material: price -should be number only- change keypad | Done | Ganesh |  |  | fixed
Tracking
1 | Testing for Live tracking | Open |  |  | 3
Create Quote
1 | Placeholder for Days, goes up to overlap the above line (On entering the Time Required) | Done | Pushkar |  |  | fixed
2 | In select material Qty and cost overlap to the below line(first time open the screen) | Done | Ganesh | Share screenshort |  | fixed
Task done
1 | app getting crashed after image upload from camera in task details screen | Done | Ganesh |  |  | fixed
2 | upload image functionality is not working in task done screen | Done | Ganesh |  |  | fixed
3 | while uploading image or video display loader in task done screen | Done | Ganesh |  |  | fixed
4 | if no media is uploaded then need to show message to upload first | Done | Ganesh |  |  | Pending
Notification
1 | Notification not working | Done | Ganesh |  |  | Pending
Misc
1 | Device token issue | Done | Vartika |  | 4 | fixed
2 | Ios build map issue | Open |  |  |  | Pending
50.5

## Consumer App-issue
sr | issue | status | priority | time in hrs(for android & iOS) | Reported by | Responsible | Developer comment | Developer 2 Comment | PM comment
Splash screen
1 | slash screen need to change as per design with text, check design here: http://design.neosofttech.in/67/homeservice/homeserviceapp.html | close | low | 4 | Sandip | Priyank | Done
Login
1 | otp auto detect while login not working on android 8, its working on service provider app | fixed | low | 0.3 | Sandip | Ashwini | Done | Fixed | Fixed
2 | login screen - cursor should be center align for country code and mobile no both | fixed | low | 1 | sandip | priyank |  | Fixed | Fixed
3 | while entering mobile no, I am able to enter . and , | Fixed | medium | 0.5 | sandip | Ashwini | done | Fixed | Fixed
4 | user can enter more than 10 digit in mobile no | Fixed | medium | 0.5 | sandip | Ashwini | done | Fixed | Fixed
5 | when loggedin using facebookl, and if otp is invalid, it takes to signup screen again. it should not navigate anwhere so user can try resend otp option again | close | high | 4 | sandip | priyank | done | Fixed | Fixed | sagar
6 | not able to signup using mobile no | Fixed | high | 3 | Sandip | Ashwini |  | Fixed | Fixed | sagar
7 | while open app showing one alert | close | medium |  | Ganesh | priyank | Done | Fixed | Fixed
8 | Login screen should not show after open app( if user is alredy register) | close | medium |  | Ganesh | priyank | Done | Fixed | Fixed | sagar
9 | Register:after getting otp app is crashed while signup customer by using google | close | high |  | Ganesh | ashwini | done | Fixed | pending
10 | when customer looged by using google and facebook device id getting null | close | high |  | Ganesh | ashwini | done | Fixed | Fixed | sagar
left sidebar
2 | if link from left side bar, then gray background should wrap complete width | Done | high | 0.3 | sandip | Ashwini | done | Fixed | Fixed
3 | move profile link below dashboard | Done | high |  | sandip | Ashwini | done | Fixed | Fixed
4 | can not edit address :show error - can't extract geo keys- have to kill app | Done | high |  | sandip | Ashwini | done | Fixed | fixed
5 | edit address box width not fixed it changes based on content length | Done | high |  | sandip | Ashwini | done | Fixed | fixed
6 | remove manage cards | close |  |  | sandip | Ashwini | done | Fixed | Fixed
7 | contact us - if no contact request added it show blank squar box below body | Done | low | 0.3 | sandip | Ashwini | done | Fixed | Fixed
8 | update edit address screen, it should have same ui as add address | Done | high | 0.3 | sandip | ashwini | done | Fixed | Fixed
9 | there is no way to add address title like office or home. it alway address type as home | Done | high | 0.3 | sandip | ashwini | done | Fixed | Fixed
10 | Customer can add maximum 10 address. | close | high | 0.3 | sandip | ashwini | done | Fixed | Fixed
11 | Personal info: user should be able to change mobile no but will get otp once otp is verified mobile no will be changeed | close | high | 5 | sandip | ashwini | done | Fixed | Fixed | sagar
12 | personal info: no need of city to be shown edit personal info | close | medium | 0.5 | sandip | ashwini | done | Fixed | Fixed
13 | if I registered using facebook or google, it shows credit points 0, which should be 100 | close | high | 5 | Sandip | ashwini/pushkar | done | Fixed | Fixed
14 | edit address show location pointer to current address, which should show to actual address | close | high |  | Sandip | Ashwini | done | Fixed | Fixed
15 | in edit address location is still showing empty, as discussed before it should show actual address | close | medium |  | Sandip | Ashwini | done | Fixed | Fixed
16 | in edit address if i click on change address and click on use current location, nothing happens, it should set current location | close | high |  | sandip | Ashwini | done | Fixed | Fixed
17 | If search location on map it shows location pointer on map which is correct, but now if i move location pointer and save address. it still not saving updated pointer location it show location which found in search | close | high |  | sandip | Ashwini | done | Fixed | Fixed
18 | in add address if i select location and add address and don't select city and don't enter zipcode it shows validation error and which is fine, but now if i click ok, it shows scrolling loading icon on screen so now i have to kill app | close | high |  | sandip | Ashwini | done | Fixed | Fixed
19 | On create request screen, change address from dropdown location marker not display in map for iOS | close |  |  |  | ashwini | done | Fixed
Create Request
1 | App should show current location on dashboard | close | high | 7 | sandip | ashwini | done | Fixed | Fixed
2 | The location feature will allow the customer to change their location manually by selecting the “Change” link and then entering the name of location. The location field will have auto-complete feature using the Google Places API. (As shown in figure 8. | close | high | 8 | sandip | ashwini | done | Fixed | Fixed
3 | select location screen should show previous search result as welll | close | low | 6 | sandip | priyank | done | Fixed | Fixed
4 | if I set location on dashhboard it show on map on create request screen, but now if came back on dashboard and use my current location, it changes location on dashboard but on not the map on create request scren | close | high |  | sandip | ashwini | done | Fixed | Fixed
Create Request
7 | Google map is not visible | close | high |  | sandip | shushant | done | Fixed | Fixed
8 | when click on request now getting device token error and after that request now doen't work | close | high | 0.3 | sandip | ashwini | done | Fixed | Fixed
9 | Request now not working | close | high | 0.3 | sandip | ashwini | done | Fixed | Fixed
10 | need space between payment type and request now button | close | high | 0.3 | sandip | ashwini | done | Fixed | Fixed
11 | on request later getting validation error | close | high | 0.3 | sandip | ashwini | done | Fixed | Fixed
12 | on selecting address from dropdown wrong location shown on map | close | high | 0.3 | sandip | ashwini | done | Fixed | Fixed
13 | Request later screen: chang date format to dd-mm-yyyy and time to mm:ss | close | medium | 0.3 | Sandip | ashwini | done | Fixed | Fixed
14 | consumer app crashed after service provider accepted service request | close | high | 7 | sandip | priyank | done | Fixed | Fixed
15 | media type value should be before but getting after while creating new request | close | high |  | Ganesh | ashwini | done | Fixed | Fixed
Request Details Screen
1 | Provider is already reached the location, still no specific details is maintained | close | high | 8 | Pushkar | Shushant | done | pending
2 | Next button should be disabled untill we reach the required step. | close | high | 0.3 | Pushkar | ashwini | done | Fixed | Fixed
3 | Provider only accepted, but app shows the next step with green tick (Provider Arrived) | close | high | 0.3 | Pushkar | priyank | done | Fixed | Fixed
4 | Change Language spelling error in placeholder, dropdown in drawer | close | high |  | Pushkar | ashwini | done | Fixed | Fixed
5 | Make the drawer's items clikable with full width flash | close | high |  | Pushkar | ashwini | done | Fixed | Fixed
6 | After quote accept , do not show task detail screen until service provider complete task done functionality | close |  |  | Ganesh | ashwini | done | Fixed | Fixed
7 | Request Details: check service provider arrived After start to job by service Provider | close |  |  | Ganesh | ashwini | done | Fixed | Fixed
8 | there is no way to tracker service provider location on consumer app | close | high | 24 | Sandip | Pratham |  | Fixed
9 | if service provider leave for job, on consumer app it shows 'Service provider arrived' | close | high | 5 | Sandip | priyank | Done | Fixed | Fixed
10 | Add option to check provider location at service request accepted | close |  | 5 |  | pratham |  | Fixed
11 | if app should show all details like total amount, credit point used, coupon amount and total payable amount on payment confirmation page | close |  | 6 | Ganesh | Ashwini | done | Fixed | Fixed
12 | based on push notification comming task status should be updated accordingly, now user has to refresh screen manually | open | high | 24 | Ganesh | Anurag |  | pending
13 | Live tracking and Testing | close | high | 24 |  | Pratham |  | Fixed
14 | scroll while add review comment & test on multiple devices | close |  | 5 | Ganesh | priyank | Done | Fixed | Fixed
15 | Check colour code for date | close |  |  | Ganesh | priyank | Done | Fixed | Fixed
16 | Maintain progress value paid and provider_review in request flow | close |  |  | Ganesh | priyank | Done | Fixed | Fixed
17 | After Review Complaint functionality is not working | close | high |  | Ganesh | priyank | Done | Fixed | Fixed
18 | Request details is not center on the screen | close |  |  | Ganesh | priyank | Done | Fixed | Fixed
19 | After payment done navgation on screen issue | close |  |  | Ganesh | priyank | Done | Fixed | Fixed
Quote Details
1 | Quote is already accepted, then we should not have Accept/Reject buttons | close | high | 0.3 | Pushkar | ashwini | done | Fixed | Fixed | sagar
2 | After Rating date is not showing proper fromat | close |  |  | Ganesh | ashwini | done | Fixed | Fixed
3 | Date format is not showing properly | close |  | 0.3 | Ganesh | priyank | Done | Fixed | Fixed
4 | it showing message Quote_provided need to fix with proper message | close | high | 3 | sandip | ashwini |  | Fixed | Fixed | sagar
5 | Can not find way to accept or reject Quote | close | high | 3 | sandip | priyank |  | Fixed | Fixed | sagar
Task Details
1 | Date format is not showing properly | close |  | 0.3 | Ganesh | priyank | Done | Fixed | Fixed
2 | Task Details: page is loading | close | high |  | Ganesh | ashwini | done | Fixed | Fixed
3 | Task Details: task details change status with actual readable message | close |  |  | Sagar | ashwini
Review
1 | If comment not add by customer not showing proper error message | close |  |  | Ganesh | ashwini | done | Fixed | Fixed
2 | Request Details:After comment provided by customer shown invalid date | close |  | 1 | Ganesh | priyank | Done | Fixed | Fixed
3 | manage service provider review and customer_review in request details flow | close |  | 5 | Ganesh | priyank | Done | Fixed | Fixed
4 | After review done, review status not shown in request details | close |  |  | Ganesh | priyank | Done | Fixed | Fixed
5 | After raise complaint review date is not shown properly | close |  |  | Ganesh | ashwini | done | Fixed | Fixed
6 | raise complaint handle empty string | close |  |  | sagar | ashwini | done | Fixed
7 | after review provided by service provider flow should be maintained | close |  |  | Ganesh | Pratham |  | Fixed
Change Language
1 | spelling mistake of arabic language | close |  |  | Ganesh | ashwini | done | Fixed | Fixed
2 | After change language the confirmation popup not closed | close |  | 3 | Ganesh | priyank | Done | Fixed | Fixed
3 | Change Language Dropdown overlaps "Refer a friend" tab [dropdown can go down on its click] | close |  |  | Pushkar | priyank | Done | Fixed | Fixed | sagar
4 | when click on change language and click on "no" button, then in drawer side bar language text is changed t | close |  |  | Pushkar | priyank | Done | Fixed | Fixed | sagar
| My Requests | [9 empty] | Change Language | Change Language
1 | manage pending , ongoing and completed request | close |  |  | Ganesh | Priyank | Done | Fixed | Fixed
2 | If there is no any request creating by customer then it should show proper message on screen | close |  |  | Ganesh | Priyank | Done | Fixed | Fixed
Dashboard
1 | User location permission popup is showing every time after app open | close |  |  | Ganesh | Priyank | Done | Fixed | Fixed
2 | Category Search (message should be as per mentioned in SRS) | close |  |  | Pushkar | Ashwini | done
3 | Routing Navigation issue | close |  |  | Ganesh | Priyank | Done | Fixed | Fixed
4 | getting continue notification to service provider | close |  |  | Ganesh | Anurag |  | Fixed
5 | Foreground Notification refresh issue | open |  |  | Ganesh | Anurag |  | pending
Signup
1 | Restructuring signup flow as per srs | Open |  |  | Ganesh | Ashwini
2 | drawer position issue for arabic language | close |  |  | ashwini | ashwini | done | Fixed | Fixed | sagar
3 | Picker issue for arabic language | close |  |  | ashwini | anurag | No third patry library support RTL for Picker so in next phase we wiil do custom picker for RTL support
4 | field validation for mobile number in signup page | close |  |  | Ganesh | ashwini | done | Fixed
Profile
1 | Personal Information: its shows en in change language dropdown when first time open screen | close |  |  | Ganesh | Pratham |  | Fixed
|  |  | total hrs | 168.6

## Service Provider app
WBS NUMBER | TASK TITLE | DURATION (hrs) | Responsible | DURATION (Weeks) | REMARKS
1 | Users |  | Vartika | 2019-03-09
1.1 | Splash Screen | 2
1.2 | Login- using phone number | 1
1.3 | Auto detection of otp | 10
1.4 | Resend otp | 6
1.5 | Manual logout | 1
2 | Dashboard |  | vartika
2.1 | Task List according to service category | 0 |  |  | Working
2.2 | Provider can accept and decline the request | 0 |  |  | Working
| Service Provider will be able to filter the tasks | 0 |  |  | Working
3 | Request Detail |  | Vartika | 17/9/2019
3.1 | Request summary - showing request details, view images and videos and showing customer contact details and location on map | 18 | Vartika |  | no screen for user detail.and no images etc.
3.2 | Request/Process Status | 1
3.3 | Service Request Accepted | 1
3.4 | Leave for Job Location - start | 1
3.5 | send lat and long on click of start button to api and stop on click of cancel, no response , reach events | 30 | vartika | 24/9/2019,
3.6 | send push notification on click of reaching customer location (deep linking) | 18 | pratham | 24/9/2019
3.7 | cancel request in case of emergency with a reason. | 1
3.8 | no response - if customer not avaiable to his location | 1
3.9 | Submit Quote - by adding material const, charges and comment | 2
3.10 | Quote accepted/cancel | 1
3.11 | Task Reschedule | 10 |  |  | new functionality
3.12 | Task Done - upload/capture images and videos of same | 9 |  |  | new functionality
3.13 | Payment Done - in case of card payment it will be automatically done once task status marked as done and in case of case servicer provider will make it as done | 2 | vartika
3.14 | Review customer by service provider | 3
5 | Side menu
6 | Profile Screen |  | Pratham Sharma | 2019-04-09
6.1 | Manage address | 2
6.2 | Manage personal information | 2
6.3 | Change language | 15
7 | Statistics Screen |  | pratham | 24/9/2019
7.1 | Filter by year | 1
7.2 | No of tasks accepted | 1
7.3 | No of task rejected | 1
7.4 | Cash payments history | 1
7.5 | Card Payments history | 1
8 | Static Pages |  | Pratham Sharma
8.1 | Faq | 3
8.2 | Contact Us | 3
9 | Refer Friend |  | Pratham Sharma | 29/8/2019
9.1 | Share link on Facebook, Instagram, Twitter and Google+” | 10
10 | Notifictaions |  | Pratham Sharma | 2019-09-09
10.1 | Request created by customer | 1
10.2 | Quote accepted by customer | 1
10.3 | Payment done successfully | 1
| TOTAL | 161
| Total days (9hrs/day) | 17.8889
| Total weeks (5days/week) | 3.5778

## consumer app translation
sr | english | arabic
1 | login | تسجيل الدخول
| Success | نجح
| success | نجح
| Error | خطأ
| error | خطأ
| SAR | ريال سعودي
| Cancel | إلغاء
| Accept | قبول
| Reject | رفض
| Next | التالي
| Amount | القيمة
| Submit | إرسال
| Close | إغلاق
| Pay | الخروج
| Logout | تطبيق
| Apply | التطبيقية
| APPLIED | لوحة القيادة
| DashBoard | لوحة القيادة
| Requests | طلبات
| Profile | الملف الشخصي
| Refer a Friend | أوص أحد الأصدقاء
| Change Laungauge | تغيير اللون
| Enter Verification Code | أدخل رمز التحقق
| We have sent verification code on | لقد أرسلنا رمز التحقق على
| Resend OTP | إعادة إرسال OTP
| Login | دخول
| Register | التسجيل
| Don't have an Account? | ليس لديك حساب؟

## HSA Admin
WBS NUMBER | TASK TITLE | DURATION (hrs) | DURATION (Weeks) | REMARKS
1 | Dashboard
| Dashboard count integration as per calculation | 4
| Graph integration as per calculation | 8
2 | Reports |  |  | Integration of reports are Done. Need to test with proper user input and calculation (which pending from backend )
| Rating | 6
| Service Request | 8
| Active Time | 6
| Time Availability | 6
3 | Manage Service Request | 50 |  | - Edit Service request with respect to service / customer app changes
| total hrs | 88
| days | 9.7778
| week | 1.9556
| TOTAL | 187.7333
| Total days (9hrs/day) | 20.8593
| Total weeks (5days/week) | 4.1719

## HSA informative site
WBS NUMBER | TASK TITLE | DURATION (hrs) | DURATION (Weeks) | REMARKS
1 | Create informative site
1.1 | informative site with ios and android app links to download | 16
1.3 | contact us page | 10
Note: Design will be provided
| total hrs | 26
| days | 2.8889

## HSA Backend api
Consumer App
Screens | Description | DURATION (hrs) | DURATION (Weeks) | REMARKS
Login | Facebook Login | 6 |  | DONE
Login | Google Login | 6 |  | DONE
OTP verification screen | OTP sending works inconsistently | 5 |  | Done
Create request | On uploading image/video, app freezes | 10 |  | Done
Create request: payment flow | - On selecting card payment and pay, it's gives error | 7
Create request: payment flow | - If request is raised and servicer provider don't accept that in set threshold time which is 60 sec now
Create request: payment flow | - its show amount as NAN, should show N.A | 4 |  | Done - frontEnd now needs to use parseInt(cost) to get it properly rendered
Address Search | Address feed on Create Request Page | 5 |  | DONE
My Profile - manage Address | - on add address screen, on tapping submit button multiple times, its add address those many times | 4
My Profile - manage Cards | - It showing hardcoded list of cards | 8
| - deleting card not working |  |  | PAYFORT NOT SUPPORTING
- default card selection not implemented
My Profile - Change Personal info | - changing mobile no - otp verification is not implemented | 8
My Profile - Credits | - Not implemented | 8 |  | DONE
Category | Category Search Not Implemented | 5
Notifications | - Not implemented | 8
Live Tracking Feature Missing | - Not implemented | 25
Instagram (logo plus feature) missing, Also, G+ is now no longer working (we should get it removed after client confirmation) |  | 8
Error Msg (Popups) | "Tranaction Failed" ------> "Transaction Failed" | 1
Service Provider
Screens | Description | DURATION (hrs) | DURATION (Weeks) | REMARKS
Dashboard/ My task | - Registered as a new service provider and found other service provider's request in My Profile | 3
Dashboard/ My task | - Could not see Service Amount on dahsboard screen | 2
| - On rejecting request it shows message `Service request accepted`. | 1
Dashboard/ My task | Should also show proper message and a box to add comment reason for rejecting. | 6
Request Details - Request Summary | - Could not see service category, order id, media files | 4
Notification Feature | Not Implemented | 12
Statistics Page | Missing Credit Card Payment received bar - Front + BackEnd | 8
Refer a friend | Not Implemented | 5
My profile - personal info | user should not able to update email, mobile and city, it should be managed by administrator | 5
Request Summary - Quote Accepted | - there is no way to reschedule task after accepting Quote | 6
| - there is no way to requote as mentioned in SRS | 6
Request Summary - Submit Quote | - there is no way to remove material once added | 5
Request Summary - Request Accept | - there is no provision for service provider to notifiy customer that he is reached to customer's address | 4
| - there is no provision to notify customer service provider reached to customer address | 2
| - there is no provison to cancel request once accpeted in case of emergency | 4
| - If service provider reaches customer location and doesn’t find any contact person they can mark status as “No Response”. | 3
| total | 194